## Backlog do Produto
Backlog do Produto
Ranking | Priority | User Story | Story Points | Status
1 | CRITICAL | As a manager/analyst, I want to collect export and import data from Brazilian states and municipalities of the state of São Paulo. | 6 | IN PROGRESS
2 | HIGH | As an analyst, I want this data to be readable using the Python programming language. | 5 | TO DO
3 | HIGH | As an analyst/client, I want this data to be visualized through a dashboard developed in Power BI | 4 | TO DO
4 | HIGH | As a manager, I want a report to be generated covering all processes carried out in the project. | 4 | TO DO
5 | MEDIUM | As a client, I want the data, reports, and results to be available on the GitHub platform. | 2 | IN PROGRESS
6 | MEDIUM | As a manager, I want to organize the tasks linked to the projects using the Jira tool. | 2 | IN PROGRESS
7 | MEDIUM | As an analyst/client, I want the dashboard to contain filters related to transport modes, states, and municipalities. | 3 | TO DO
8 | MEDIUM | As a manager, I want this data to be updated periodically. | 3 | TO DO
9 | LOW | As an analyst, I want dashboard templates to be created so they can be used as future references. | 2 | IN PROGRESS
10 | LOW | As a client, I want to understand the purpose of the proposed project. | 1 | IN PROGRESS
11 | LOW | As a client, I want to know what to expect from this project in the future. | 1 | IN PROGRESS
12 | LOW | As a client, I want the project results to be accessible and published externally for academic and research purposes. | 1 | TO DO

## Backlog - 1° Sprint
Backlog - 1º Sprint
Ranking | Priority | User Story | Story Points | Status
1 | CRITICAL | As a manager/analyst, I want to collect export and import data from Brazilian states and municipalities of the state of São Paulo. | 6 | IN PROGRESS
2 | HIGH | As an analyst, I want this data to be readable using the Python programming language. | 5 | TO DO
5 | MEDIUM | As a client, I want the data, reports, and results to be available on the GitHub platform. | 2 | IN PROGRESS
6 | MEDIUM | As a manager, I want to organize the tasks linked to the projects using the Jira tool. | 2 | IN PROGRESS
9 | LOW | As an analyst, I want dashboard templates to be created so they can be used as future references. | 2 | IN PROGRESS
10 | LOW | As a client, I want to understand the purpose of the proposed project. | 1 | TO DO
11 | LOW | As a client, I want to know what to expect from this project in the future. | 1 | TO DO

## Backlog - 2° Sprint
Backlog - 2º Sprint
Ranking | Priority | User Story | Story Points | Status
3 | HIGH | As an analyst/client, I want this data to be visualized through a dashboard developed in Power BI | 4 | TO DO
7 | MEDIUM | As an analyst/client, I want the dashboard to contain filters related to transport modes, states, and municipalities. | 3 | TO DO
8 | MEDIUM | As a manager, I want this data to be updated periodically. | 3 | TO DO

## Backlog - 3° Sprint
Backlog - 3º Sprint
Ranking | Priority | User Story | Story Points | Status
4 | HIGH | As a manager, I want a report to be generated covering all processes carried out in the project. | 4 | TO DO
12 | LOW | As a client, I want the project results to be accessible and published externally for academic and research purposes. | 1 | TO DO