## Backlog do Produto
Backlog do Produto
Ranking | Priority | User Story | Story Points | Status
1 | CRITICAL | As a supply chain and trade analyst, I aim to collect foreign trade data (exports and imports) at both the state level across Brazil and at the municipal level within the state of São Paulo. | 6 | DONE
2 | HIGH | From a logistics analytics perspective, I intend to process, store, and visualize these datasets using the Python programming language, leveraging the Pandas library within the Google Colab environment. | 5 | TO DO
3 | HIGH | As a public policy manager, I want a Power BI dashboard that consolidates export and import data from all Brazilian states and the municipalities of São Paulo, covering the period from 2023 to 2025. | 4 | TO DO
4 | HIGH | As a manager, I would like to monitor the entire process of this project through a written report developed in Microsoft Word, formatted according to ABNT academic standards. | 4 | TO DO
5 | MEDIUM | As a manager/client, I want all spreadsheets, dashboards, and reports to be publicly available and easily accessible on the GitHub platform. | 2 | IN PROGRESS
6 | MEDIUM | As a public policy manager, I request that the dashboard include filters to segment the information by transport modes, states, and municipalities. | 3 | TO DO
7 | MEDIUM | As a manager, I request that the data presented, along with the dashboard, be constantly updated to ensure better monitoring of the requested information. | 3 | TO DO
8 | LOW | As a public policy manager/client, I want the purpose of the proposed project to be detailed, as well as its impact on the country’s current situation. | 1 | DONE
9 | LOW | As a public policy manager/client, I would like a detailed description of the project’s future outlook and what can be expected from its results. | 1 | DONE
10 | LOW | As a public policy manager, I would like the project’s results to be publicly accessible, in order to enable research and the development of future initiatives. | 1 | TO DO

## Backlog - 1° Sprint
Backlog - 1º Sprint
Ranking | Priority | User Story | Story Points | Status
1 | CRITICAL | As a supply chain and trade analyst, I aim to collect foreign trade data (exports and imports) at both the state level across Brazil and at the municipal level within the state of São Paulo. | 6 | DONE
5 | MEDIUM | As a manager/client, I want all spreadsheets, dashboards, and reports to be publicly available and easily accessible on the GitHub platform. | 2 | DONE
8 | LOW | As a public policy manager/client, I want the purpose of the proposed project to be detailed, as well as its impact on the country’s current situation. | 1 | DONE
9 | LOW | As a public policy manager/client, I would like a detailed description of the project’s future outlook and what can be expected from its results. | 1 | DONE

## Backlog - 2° Sprint
Backlog - 2º Sprint
Ranking | Priority | User Story | Story Points | Status
2 | HIGH | From a logistics analytics perspective, I intend to process, store, and visualize these datasets using the Python programming language, leveraging the Pandas library within the Google Colab environment. | 5 | IN PROGRESS
3 | HIGH | As a public policy manager, I want a Power BI dashboard that consolidates export and import data from all Brazilian states and the municipalities of São Paulo, covering the period from 2023 to 2025. | 4 | IN PROGRESS
6 | MEDIUM | As a public policy manager, I request that the dashboard include filters to segment the information by transport modes, states, and municipalities. | 3 | TO DO
7 | MEDIUM | As a manager, I request that the data presented, along with the dashboard, be constantly updated to ensure better monitoring of the requested information. | 3 | UNDER REVIEW

## Backlog - 3° Sprint
Backlog - 3º Sprint
Ranking | Priority | User Story | Story Points | Status
4 | HIGH | As a manager, I would like to monitor the entire process of this project through a written report developed in Microsoft Word, formatted according to ABNT academic standards. | 4 | TO DO
10 | LOW | As a public policy manager, I would like the project’s results to be publicly accessible, in order to enable research and the development of future initiatives. | 1 | TO DO